## Mitigation Rec Summary
Proposed Mitigation Plan | Risk | Implementation Phasing | Mitigation Effort | Complete | Comments
|  | 1 | 1 | X
|  | 1 | 2 |  | When Jill retires, won't necessarily need another CPA.
|  | 1 | 2 |  | Current thoughts that Amber could be next in line.
|  | 1 | 3 |  | Concerns with WiFi Security concerns on laptops. Discussion point with Pinnacle to see how to mitigate wireless concerns. 12/17/20 - Looking at new laptops for Kelly's workstation. Will move Kelly's old laptop to central control station.
|  | 1 | 4 |  | Still waiting for quote. 12/17/20 - PRIORITY FOR 2021. Looking at option to have electrician put in plug to utilize portable generator for power needs.
|  | 1 | 5 |  | Backup for NatPay in Phase 1. Cyberpay/Pinnacle in Phase 3. 12/17/20 - Will f/u in early 2021. Have ~20 customers that are "sames" they can test with.
|  | 2 | 2 |  | Now putting paper docs in fire safe every night. Long term plan (Phase 4): convert paper files to electronic system. Need to investigate electronic options. 12/17/20 - Process for putting files in safe is set. Now need to develop and implement process
|  | 2 | 3 |  | Could be lower priority. Need understanding of their wills, and plan for transfer of PDP if Pat dies. 12/17/20 - In process with lawyers to finalize.
|  | 2 | 3 | X | Need template that matches CyberPay and Timeworks improt needs 12/17/20 - Have excel template in place.
|  | 2 | 4 |  | Current worry about COTA Pay, due to payment lags that COTA Pay has built in to their process. Want to find another option instead of COTA Pay.
|  | 3 | 3 | X | 12/17/20 - Have location at Pinnacle if needed. Also able to utilize space at Pat's various properties if needed.
|  | 3 | 3 |  | Need feedback from Pinnacle when ready to address.
|  | 3 | 3
|  | 3 | 3 | X | 12/17/20 - Will just go to Post Office.
|  | 3 | 5
|  | 4 | 1 | X | Tested call frowarding. Works as planned.
|  | 4 | 2 |  | Could bring Angel back later in the year as things return to normal.
|  | 4 | 2 |  | Ties with long term need for electronic documentation system.
|  | 4 | 2 | X | Have check printer and MICR cartridge at Kelly's house.
|  | 4 | 3 | X | Pinnacle has said they can have servers back up and running within 4 hours if both happened to go down. 12/17/20 - At next server upgrade, Pinnacle to provide options for cloud and physical server possibilities.
|  | 4 | 5 | X | Unlikely to get everyone on direct deposit. Paper checks are actually desirable with some clients. Can plan transition of existing clients to online portal from a time tracking perspective.

## Risk Listing
CLIENT Risk Listing
Risk | Risk Details | Likelihood (0-100%) | Impact (0-100%) | Risk Score | Description of Existing Control or Countermeasure | Proposed Mitigation Plan | Mitigation Effort (0-5 0= not doing 5=extremely difficult) | Priority Score | Implementation Phasing
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 0 | #DIV/0! | N/A
|  | 0% | 0% | 0% |  |  | 1 | 0 | 1
|  | 50% | 100% | 50% |  |  | 5 | 0.1 | 1
|  | 20% | 20% | 4% |  |  | 3 | 0.013333 | 1
|  | 0% | 0% | 0% |  |  | 2 | 0 | 1
|  | 0% | 0% | 0% |  |  | 2 | 0 | 1
|  | 0% | 0% | 0% |  |  | 4 | 0 | 1
|  | 0% | 0% | 0% |  |  | 4 | 0 | 2
|  | 0% | 0% | 0% |  |  | 3 | 0 | 2
|  | 0% | 0% | 0% |  |  | 5 | 0 | 2
|  | 0% | 0% | 0% |  |  | 2 | 0 | 2
|  | 0% | 0% | 0% |  |  | 3 | 0 | 2
|  | 0% | 0% | 0% |  |  | 3 | 0 | 3
|  | 0% | 0% | 0% |  |  | 3 | 0 | 3
|  | 0% | 0% | 0% |  |  | 3 | 0 | 3
|  | 0% | 0% | 0% |  |  | 3 | 0 | 3
|  | 0% | 0% | 0% |  |  | 3 | 0 | 3
|  | 0% | 0% | 0% |  |  | 2 | 0 | 4
|  | 0% | 0% | 0% |  |  | 1 | 0 | 4
|  | 0% | 0% | 0% |  |  | 5 | 0 | 4
|  | 0% | 0% | 0% |  |  | 2 | 0 | 4
|  | 0% | 0% | 0% |  |  | 3 | 0 | 4
|  | 0% | 0% | 0% |  |  | 2 | 0 | 4

## Pivot Table Chart
CLIENT Mitigation Benefit-Effort Matrix